## Spring Backlog
User Story ID | Sprint Backlog Item | Assign To | Estimated | Estimated Effort Remaining at the end of Day…
Effort-hour
|  |  |  | 1 | 2 | 3 | 4
1 | As a Resource Centre staff member, I want to be able to input details of laptops or digital cameras into the system, so that I can easily track the ownership and specifications of each device. | Student A and B | 24
4 | As a Resource Centre staff member, I want to be able to view a list of all available laptops and digital cameras so that I can quickly see which items are currently available for loan. | Student C and D | 16
6 | As a Resource Centre staff member, I want to be able to input loan details for laptops and digital cameras, including the student's name, asset number of the item, and due date, so that I can easily track the loan records. | Student E and F | 32
7 | As a Resource Centre staff member, I want to be able to mark an item as checked in when a student returns it, so that I can keep accurate loan records. | Student C and D | 32
| Total story point: 14 | Total effort-hour: | 104 | #N/A | #N/A | #N/A | #N/A

## Sprint Burndown Chart
Day | Ideal/Estimated Work Remaining | Actural Work Remaining
0 | 104 | 104
1 | 78 | #N/A
2 | 52 | #N/A
3 | 26 | #N/A
4 | 0 | #N/A